## Plan Progress
Task | Responsible | Start | End | Days | Complete | time axis 2017-01-17 to 2017-03-28
 | time axis 2017-01-17 to 2017-03-28
Requirements |  | 2017-01-19 | 2017-01-25 | 5 | 10%
Discovery |  | 2017-01-19 | 2017-01-22 | 2 | 20%
Kick-Off Meeting |  | 2017-01-19 | 2017-01-19 | 1 | 30%
Sizing |  | 2017-01-23 | 2017-01-27 | 5 | 40%
Document Architecture |  | 2017-01-27 | 2017-02-03 | 6 | 50%
Approval |  | 2017-02-03 | 2017-02-06 | 2
Internal Review |  | 2017-02-03 | 2017-02-06 | 2
Client Signoff |  | 2017-02-03 | 2017-02-06 | 2
Build |  | 2017-02-06 | 2017-02-25 | 15
Request Server Hardware |  | 2017-02-06 | 2017-02-14 | 7
Ops Manager Server |  | 2017-02-06 | 2017-02-14 | 7
Replica Sets and Shards |  | 2017-02-06 | 2017-02-14 | 7
Config Servers |  | 2017-02-06 | 2017-02-14 | 7
Install Software |  | 2017-02-15 | 2017-02-18 | 3
Install Ops Manager |  | 2017-02-14 | 2017-02-16 | 3
Install MongoDB on Shards / Replica Sets |  | 2017-02-16 | 2017-02-19 | 2
Onboard Shards / Replica Sets |  | 2017-02-19 | 2017-02-20 | 1 |  | 0
Install Application Software |  | 2017-02-14 | 2017-02-17 | 4 |  | 0
Test Application Software |  | 2017-02-17 | 2017-02-20 | 2 |  | 0
Load Test MongoDB |  | 2017-02-20 | 2017-02-24 | 5 |  | 0
Document Results |  | 2017-02-24 | 2017-02-25 | 1 |  | 0
Build Complete - Signoff |  | 2017-02-25 | 2017-02-25 | 0 |  | 0
Launch POC |  | 2016-12-18 | 2016-12-27 | 7 |  | 0
Soft Launch Rollout |  | 2016-12-19 | 2016-12-28 | 8 |  | 0
Final Launch sequence testing and soft launch go live |  | 2016-12-20 | 2016-12-29 | 8 |  | 0
Post Soft Launch monitoring |  | 2016-12-21 | 2016-12-18 | -3 |  | 0
Full Rollout |  | 2016-12-22 | 2016-12-19 | -4 |  | 0
Go-Live Readiness Checkpoint |  | 2016-12-23 | 2016-12-20 | -4 |  | 0
Final Launch sequence testing and full launch go live |  | 2016-12-10 | 2016-12-21 | 8 |  | 0
Post Full Launch monitoring |  | 2016-12-25 | 2016-12-22 | -2 | 50% | -1
Training and Communication |  | 2016-12-26 | 2016-12-23 | -2 |  | 0
Early Program Announcements |  | 2016-12-27 | 2016-12-24 | -2 |  | 0
Develop Training and Comm Materials |  | 2016-12-28 | 2016-12-25 | -3 |  | 0
System training |  | 2016-12-29 | 2016-12-26 | -4 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
96
Today's Date | 2017-01-17 | 400%
Start Date | 2017-01-17
Projected End Date | 2017-02-28
Total Man Days | 96
Project Duration | 75
<Your Project Name Here>

## Sheet2
Nonworking Date | Reason
2012-05-21 | MetLife Holiday
2012-05-22 | MetLife Holiday
2012-05-23 | MetLife Holiday
2012-05-24 | MetLife Holiday
2012-05-25 | MetLife Holiday
2012-05-28 | Memorial Day

## Sheet3
Legend
| Active Tasks | Tasks Overdue Start
| Completed Tasks (100%) | Tasks Running Late
| Non-Working Day | Non-Working Day
| Current Day | Current Day
Beyond Projected Last Day